## Test Cases
Test Scope and Test Cases
TS #1 - Student Application, Payment, User Creation and Single Log In
TC_01 | Enrol a student via Student Portal (including data validation in CRM)
TC_02 | Enrol a student manually in CRM (including data validation in CRM)
TC_03 | Resend log in (temp password verification email)
TC_04 | Manually create an order (invoice)
TC_05 | Log in to Student Portal (first time using temp password)
TS #2 - Verify records on Xero
TC_06 | Verify invoice record
TC_07 | Verify account record
TS #3 - Student Portal: Update Student Account
TC_08 | Update Profile Picture
TC_09 | Change Password
TC_10 | Update Social Accounts
TS #4 - Student Portal: View Grades, Payment and Documents
TC_11 | View Profile
TC_12 | View Grades (block and module enrolments, for grades - assessment should be done first)
TC_13 | View Payment
TC_14 | View Student Documents (update files first in Sharepoint)
TS #5 - Student Portal and CRM Cases
TC_15 | Submit Support Request
TC_16 | Submit Withdrawal Request
TS #6 - Course Setup and Variation including Products and Intakes
TC_17 | Publish new Course (SMS to LMS and taxonomy in CMS)
TC_18 | Add New Block with new Modules
TC_19 | Remove Block
TC_20 | Update Blocks (new module groupings)
TC_21 | Add new Module to Existing Block
TC_22 | Remove Module
TC_23 | Add New UOC to a Module
TC_24 | Remove UOC from a Module
TC_25 | Update Assessment (ie. Result Keys)
TS #7 - Course Enrolment and Variation
TC_26 | Course Enrolment and Children
TC_27 | Add new Module Enrolment
TC_28 | Add Elective
TS #8 - Academic Record and Assessment Rollup
TC_29 | Update Assessment Enrolment (Competent)
TC_30 | Update Assessment Enrolment (Not Yet Competent to Competent)
TC_31 | Verify Academic Record Update (Based on Assessment Enrolment)
TC_32 | Verify Module Enrolment Completion
TC_33 | Complete Assessment in LMS and verify record in SMS
TS #9 - Systems Navigation
TC_34 | Navigate to Course from Student Portal to LMS
TC_35 | Login to LMS and navigate to SP
TC_36 | Login to SP and navigate to LMS

## Test Scripts
Test Case # | Test Case Description | Prerequisite | Step # | Test Case Steps | Expected Result | Actual Result | Test Case Status | Additional Comments
Student Application, Payment, User Creation and Single Log In
TC_01 | Enrol a student via Student Portal (including data validation in CRM) |  | 1 | Go to Student Portal - https://portal-uat.uponline.education/ | Student Portal main page is displayed
|  |  | 2 | On the list of Course, click [Details] on the preferred course | Course Detail Page is displayed
|  |  | 3 | Click Enrol | Sign Up form is displayed
|  |  | 4 | Enter Identification details | First Name, Last Name, Email, Home Phone and DOB is entered
|  |  | 5 | Click Next | Student Details form is displayed
|  |  | 6 | Enter Postal Address details | Address details are entered
|  |  | 7 | (Optional) Enter Additional Student details | Additional Student details are entered
|  |  | 8 | Select Gender | Gender is selected
|  |  | 9 | (Optional) Select Ethnicity | Ethinicity value is selected
|  |  | 10 | Select Disability value | Disability value is selected
|  |  | 11 | Click Next | Supporting Documentation page is displayed
|  |  | 12 | Upload supporting documents | Supporting Documents are uploaded
|  |  | 13 | Click [Next] | Terms & Conditions page is displayed
|  |  | 14 | Click I agree | I agree field has been checked
|  |  | 15 | Select Payment Method | Payment method is selected
|  |  | 16 | Enter Full Name | Full Name is entered
|  |  | 17 | Click Next | Initial payment page is displayed with Invoice reference and amount to be paid
|  |  | 18 | Click Proceed to Payment | Payment Checkout form is displayed
|  |  | 19 | Enter Card details | Card details are entered
|  |  | 20 | Click Submit | Transaction details (approved) are displayed
|  |  | 21 | Click Next | Welcome message page is displayed
|  |  | 22 | Navigate to CRM > Online Learning | Default landing page is displayed
|  |  | 23 | Find and open the Opportunity record | Opportunity record is displayed
|  |  | 24 | Click on the Opportunity record dropdown option | Opportunity record dropdown options are displayed
|  |  | 25 | Change Status to Enrolled | Status is changed to Enrolled
|  |  | 26 | Click Save | Changes to Opportunity is saved. Course Enrolment and SMS Enrolment ID is created

## Test Execution Schedule
2020-06-26 | 2020-06-29 | 2020-06-30 | 2020-07-01 | 2020-07-02 | 2020-07-03 | 2020-07-06 | 2020-07-07 | 2020-07-08 | 2020-07-09 | 2020-07-10 | 2020-07-13 | 2020-07-14 | 2020-07-15 | 2020-07-16 | 2020-07-17
Initial Deployment to UAT | Course Setup and Variation including Products and Intakes |  | Academic Record and Assessment Rollup |  | Deployment for Fixes | Bug Retest |  |  | Performance Testing |  | Buffer week for additional development, enhancements, bug fixes/retest and further regression testing (if needed)
| Student Application, Payment, User Creation and Single Log In | Course Enrolment and Variation | Data Loading and Reporting |  |  |  | Deployment for Fixes | Regression Testing
| Student Portal - View Grades, Payment and Documents |  | LMS Log In and Assessment Updates
Student Records – Lead, Opportunity, and Contact
Student Portal and CRM Cases