## Documentation
Documentation that would be required for the project
Specification name: | 15 Boronia street SPECS
Drawings title | Drawing number | Revision number
GRANNY FLAT_ELEVATIONS | A.04 | B
GRANNY FLAT_SITE PLAN | A.01 | B
GRANNY FLAT_GEN NOTES | A.02 | A
GRANNY FLAT_FLOOR PLAN | A.03 | B

## Equipment
List of equipment, site accommodation and services information
Equipment list
1 | Skid Steer Loader.
2 | Backhoe Loader.
3 | Forklift.
4 | Telehandler.
5 | Scissor Lift.
Site accomodation requirements
1 | Portable buildings
2 | Designated area for management
Service information (What is required before construction starts)
1 | Electrical survey
2 | Plumbing survey
3 | Incoming mains locations

## List of materials
List of materials that would be required for the project
Concrete slab and footings
1 | Pre mix concrete
2 | Reiforcement
3 | Builders plastic
4 | Bar chairs
External and internal walls
1 | stud framing
2 | Windows
3 | Doors
4 | Door frames
Fitout
1 | Cabinetry
2 | Floor coverings
3 | Electrical fittings
4 | Plumbing fittings

## Gantt Chart
[6 empty] | 1 |  | 0 | 2021-01-21 | 2021-01-28 | 2021-02-04 | 2021-02-11 | 2021-02-18 | 2021-02-25 | 2021-03-04 | 2021-03-11 | 2021-03-18 | 2021-03-25 | 2021-04-01 | 2021-04-08 | 2021-04-15 | 2021-04-22 | 2021-04-29 | 2021-05-06 | 2021-05-13 | 2021-05-20 | 2021-05-27 | 2021-06-03 | 2021-06-10 | 2021-06-17 | 2021-06-24 | 2021-07-01
New granny flat | bar: 0
Time Period
Weekly
|  |  | Gantt Chart Dates |  |  | Yelow - Completion date
|  |  | Beginning Date | 2021-01-21 |  | Green - Complete Project
|  |  | Completion date | 2021-07-21
2021
[5 empty] | Start | End | Task | % | Jan | Jan | Feb | Feb | Feb | Feb | Mar | Mar | Mar | Mar | Apr | Apr | Apr | Apr | Apr | May | May | May | May | Jun | Jun | Jun | Jun | Jul
| Level | WBS | Task | Resource | Start Date | End Date | Duration | Complete | 21 | 28 | 4 | 11 | 18 | 25 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1
1 | P | 1 | Site Works | Task Owner | Task: 0; %: 100%
| A | 1.1 | Clear site | Earth works | Start: 2021-01-21; End: 2021-01-23; Task: 2; %: 100%
| A | 1.2 | Level Site | Earth works | Start: 2021-01-23; End: 2021-01-26; Task: 2; %: 100%
2 | P | 2 | Concrete slab and footings |  | Task: 0; %: 100%
| A | 2.1 | Site establishment | Supervisor | Start: 2021-01-26; End: 2021-01-30; Task: 4; %: 100%
| B | 2.1.1 | Set out footings and slab | Concreters | Start: 2021-01-30; End: 2021-02-03; Task: 3; %: 100%
| B | 2.1.2 | Install reo | Concreters | Start: 2021-02-03; End: 2021-02-08; Task: 4; %: 100%
| B | 2.1.3 | Pour footings and slab | Concreters | Start: 2021-02-08; End: 2021-02-11; Task: 4; %: 100%
| B | 2.1.4 | Curing time | Concreters | Start: 2021-02-11; End: 2021-03-04; Task: 16; %: 100%
3 | P | 3 | External internal walls and roof |  | Task: 0; %: 100%
| A | 3.1 | External walls | Carpentry | Start: 2021-03-04; End: 2021-03-29; Task: 18; %: 100%
| A | 3.2 | Internal walls | Carpentry | Start: 2021-03-09; End: 2021-03-29; Task: 15; %: 100%
| A | 3.3 | Roof structure | Carpentry | Start: 2021-03-29; End: 2021-04-13; Task: 12; %: 100%
4 | P | 4 | Fitout |  | Task: 0; %: 100%
| A | 4.1 | Cabinetry | Cabinetry | Start: 2021-04-16; End: 2021-04-26; Task: 7; %: 100%
| A | 4.2 | Electrical and plumbing works | Electrical | Start: 2021-04-16; End: 2021-04-29; Task: 10; %: 100%
| A | 4.2 | Flooring | Flooring | Start: 2021-04-21; End: 2021-04-29; Task: 7; %: 100%
| A | 4.3 | Painting | Painting | Start: 2021-04-24; End: 2021-05-15; Task: 15; %: 100%
| A | 4.4 | Touch ups | General labour | Start: 2021-05-17; End: 2021-05-24; Task: 6; %: 100%
| A | 4.5 | Practical completion | General labour | Start: 2021-05-29; End: 2021-05-31; Task: 1; %: 100%
| A | 4.5 | Handover | Builder | Start: 2021-05-31; End: 2021-06-01; Task: 2; %: 100%
5
Exclude Weekends
Task Duration Calculation
Include Weekends
Key

## EOT
EXTENSION OF TIME REQUEST
Costing Number
DATE: | 2021-01-21 | JOB NO: |  |  |  |  | VCR: 1
LOT NO: | 88 | HOUSE NO: | 15
SITE ADDRESS: | Springwood (Student's state/territory), 15 Boronia street
CLIENT: | Mr and Mrs McArthur
VARIATION DUE TO :
Design |  |  |  | BL Cond
Contract |  |  |  | Prestart |  | X
DA Cond |  |  |  | In-Construction
Item | Description |  |  |  | Timeframe
1 | install safety screens over all windows |  |  |  | 7
2 | Solid timber flooring to dry areas |  |  |  | 28
3 | Split aircon for heating and cooling |  |  |  | 10
| TOTAL |  |  |  | 45
Signed for Approval : | [5 empty] | Date