## Instructions
Instructions for using this workbook
Contents
This workbook contains a number worksheets that provide templates and tools to help you effectively manage risk
| Worksheet | RMF process | Description
| Context & Objectives | Establish the Context | Use this template to list your objectives, scope the context for risk management in your firm, and identify stakeholders.
| Register | Document | Use this template to document the identification, analysis & evaluation, treatment and monitoring of risks for your firm.
| Identification | Identify Risks | Provides examples of risks that are typical to small to midsize firms.
| Assessment_Likelihood | Analyse & Evaluate Risks | Lists assessment criteria for rating the likelihood, or probability, of a risk event occurring.
| Assessment_Consequence | Analyse & Evaluate Risks | Lists the assessment criteria for rating the consequence, or impact, if a risk event occurs.
| Rating Matrix | Analyse & Evaluate Risks | Lists risk ratings based on the assessed likelihood and consequence.
| Assessment_Controls | Analyse & Evaluate Risks | Lists the assessment criteria to rate the effectiveness of existing controls within your firm.
| Treatment | Treat Risks | Lists the options available for treating risks.
Using the Risk Register
 | Descriptions about what needs to be documented in each column of the Risk Register can be found in the first row after the column headings.
To display or hide this information click +/- on the left of the worksheet to expand or collapse this row.
 | Entries for the following columns can be selected from the drop-down list available:
Risk Category
Likelihood
Consequence
Control Effectiveness
Action
Status
 | The entry in the Risk Rating column will display automatically once the assessment criteria for Likelihood and Consequence have been selected.
 | Conditional formatting has been used in the Risk Register to display traffic light colours for all assessment criteria and risk ratings.
Source: Chartered Accountants Australia New Zealand. Risk Management Framework - Risk Management for Small Firms. [online] Available at: https://survey.charteredaccountantsanz.com/risk_management/small-firms/small.aspx.

## 1. Context & Objectives
Establish the Context & Objectives
Organisational objectives:
Identify organisational objectives, e.g. objectives relating to: |  | Wealth accumulation
Our business goals | 1. Increase net income to $100 000 from existing retail store in Sydney, NSW
2. Expand business operations and open a new store in Brisbane, Queensland
Target market | Toys are targeted towards children aged 0 – 10 years with those making the toy purchase being middle to high income earners and educational service providers.
Industry specialisation/unique selling point | Toys are wooden, made in Australia and environmentally friendly.
The Context:
Establish the context which might impact achieving practice objectives, e.g. factors relating to:
Internal Context | Strengths | Weaknesses | Opportunities | Threats | Stakeholders
Organisational structure | Flat management structure only two staff | No redundancy if any one gets sick | Build in more staff and knowledge retention stratgies | Loss of key business intelligence, loss of clients Lack of continuity of client service | Clients | Our products are targeted at children 0 – 10 years being bought by someone with a medium to high disposable income.
Products/services provided | Toll’s Toys sells a small range of high-quality toys. | We only sell high quality, sustainably produced toys | Position ouselves as the quality alternative and produce a new line of low priced quality products | The market is flooded with plastic toys that are not educational. Competition is cheaper | Staff | Leo Toll, Val Henderson
Technology | Use cloud storage for business records. |  | Improve use of Passords and encryption | Computer theft results in loss of financial records. | Others
Organisational culture | Leo regularly checks in with Val and he offer free courses to maintain staff skills and knowledge of the toys that are sold. |  | As staff numbers increase, formalise training and knowledge retention strategies | As staff numbers increase, new staff do not know what to do
Office premises | Premises are in a high traffic area with good visibility. | There are high rental costs. | access to more high networth customers | Increases in rent
Pandemic Response | Creating an online store |  | online Sales | Pandemic causes closure of our retail outlet.
External Context | Strengths | Weaknesses | Opportunities | Threats | Stakeholders
Geographical location | Premises are in a high traffic area with good visibility. | There are high rental costs. |  |  | Clients
Legislative/regulatory framework | Fair trading/consumer laws, employment laws, state licences, Company Law, ASIC, Taxation Law |  |  |  | Regulators | ASIC, Fair Trading etc
Economic conditions |  |  | The market is growing rapidly and there is demand in Queensland for a retail store. | A new competitor could target the same market. | Bank
Employment market |  |  |  |  | Third parties
Environmental factors | Toll’s Toys purchases its toys from ECO Creatives, a sustainable toy manufacturer in Australia. Our packaging is printed by an external provider. We package the toys on site with strict quality controls in place. | Toll’s Toys purchases its toys from ECO Creatives, a sustainable toy manufacturer in Australia. Our packaging is printed by an external provider. We package the toys on site with strict quality controls in place.
Source: Chartered Accountants Australia New Zealand. Risk Management Framework - Risk Management for Small Firms. [online] Available at: https://survey.charteredaccountantsanz.com/risk_management/small-firms/small.aspx.

## 2. Register
Risk Register
RISK IDENTIFICATION | [7 empty] | RISK ASSESSMENT |  |  | RISK TREATMENT |  |  |  | RISK MONITORING & REVIEW
Risk ID | Date Raised | Raised by | Risk Category | Event/ What could happen? | Cause | Consequence | Existing controls | Residual Risk Analysis |  |  | Action | Plan | Risk Owner | Resolve by | Method | Progress and Compliance Reporting | Status
[8 empty] | Likelihood | Consequence | Risk Rating
Enter a unique reference | Enter the date when risk first raised | Name the person who raised risk | Identify the relevant risk category | Capture the potential event with enough detail to be understood in isolation | Describe the potential causes of event occurring | Describe the main impact of risk event |  | Assess the probability of risk event occurring | Assess the plausible impact of risk event occurring | Rate the risk based on likelihood and consequence | Describe the treatment to be applied to risk | State the planned action to treat risk | Assign a Plan Owner | Enter the date by which action to be implemented | List the methods for monitoring action plan(s) and review points | Track and report on the progress of actions plan(s), and note any instances of non-compliance, breaches or near misses | Update status
1 | 2022-02-18 | Kelly Make | Human resources | No redundancy if any one gets sick | pandemic, accident, illness, death | Unavailability of experienced qualified employees | None | RARE | MAJOR | LOW |  | Build in more staff and knowledge retention strategies | Leo Toll | TBA | staff head count changes in register of updates to policies and procedures | Students do not need to complete, this is completed as progress is made, | OPEN
2 | 2022-02-18 | Kelly Make | Business | Failure to identify new opportunities | Failures to notice the market trends and to respond with product innovations. | Losses of market confidence, position and revenue. |  | POSSIBLE | MODERATE | TOLERABLE |  | On sell our products to other stores, develop new lines of entry level toys. | Leo Toll | TBA | Sales reports | Students do not need to complete, this is completed as progress is made, | OPEN
3 | 2022-02-18 | Kelly Make | Financial | Unexpected downturn of the market, low sales. | Over estimating value of goodwill and borrowing based on estimate Use inflated goodwill calculation when paying our departing Partners | Inability to service loan Reduction in value of goodwill |  | POSSIBLE | MAJOR | HIGH |  | Build buffer fund as a guard to market dips, Develop new additional markets and product lines, | Leo Toll | TBA | Monthly statements Sales reports | Students do not need to complete, this is completed as progress is made, | OPEN
4 | 2022-02-18 | Kelly Make | Business continuity | Loss or damage to office premises, office equipment and/or client records | Natural catastrophe, theft | Disruption and possible failure of business |  | POSSIBLE | MAJOR | HIGH |  | Build buffer fund as a guard, ensure insurance is adequate, paid on time and up to date | Leo Toll | TBA | Monthly statements | Students do not need to complete, this is completed as progress is made, | OPEN
5 | 2022-02-18 | Kelly Make | Technology | IT systems failure | Power outages, security breaches | Poor or disruptions of client services, loss of clients |  | POSSIBLE | MAJOR | HIGH |  | Purchase battery back up or generator for crucial systems, leverage cloud systems to allow some remote work. | Leo Toll | TBA | Purchase , leverage cloud systems to allow some remote work. | Students do not need to complete, this is completed as progress is made, | OPEN
PART B - MONITOR, CONTROL AND RECOMMEND IMPROVEMENTS
6 | 2022-02-18 | Kelly Make | Regulatory | Failure or non-compliance with regulatory, legal and policy obligations | Lack of monitoring/understanding of legislative obligations | Penalties and fines Increased scrutiny from regulators Reputational damage | Strong | UNLIKELY |  |  |  | Update policies and procedures regularly, and engage specialist if required, Ensure insurance is adequate, paid on time and up to date | Leo Toll | TBA | schedule of updates recorded in monthly reports | Students do not need to complete, this is completed as progress is made, | OPEN
7 | 2022-02-18 | Kelly Make | Stakeholder | Closure of supplier | Closure of supplier | No product to sell, less variety of products | None | LIKELY |  |  |  | Explore and record other suppliers and supply chains | Leo Toll | TBA | Record in Process documents | Students do not need to complete, this is completed as progress is made, | OPEN
8 | 2022-02-18 | Kelly Make | Governance | Business strategy does not accommodate changing market conditions | Backup plans do not cater appropriately for a wider possibilities of changes in the market | Loss of income or closure of business | Moderate | LIKELY |  |  |  | Update strategy and policies and procedures urgently | Leo Toll | TBA | strategy document and policies and procedures | Students do not need to complete, this is completed as progress is made, | OPEN
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24

## Identification
Example Risks for Practices
Context/ Category | Risk | Cause | Consequence
Business | Failure to diversify client base, i.e. a single client or client group accounts for significant portion of practice fees | Loss of key client | Loss of revenue Failure of practice
Business | Failure to deliver quality product or service | Lack of staff training Ineffective quality control and engagement review Service not delivered in a timely manner | Reputational damage Damage relationship with clients Increase in client complaints Increased scrutiny from regulators Increased likelihood of claims
Business | Loss of key staff member | Accident, illness, retirement or lack of opportunity for progression | Loss of key business intelligence, loss of clients Lack of continuity of client service
Business | Concentration of services provided in an area of advice/compliance or to a particular industry | Market conditions negatively impact client business, e.g. if majority of clients are agriculture-based and there is a drought. Change in compliance framework | Loss of significant portion of client work Failure of practice
Business | Negative comment on social media | Failure to communicate effectively with client/s | Significant loss of reputation and client fees
Business | Failure to identify new service offerings | Failure to understand the market and the requirements or market desire for new service offerings | Loss of revenue Failure of practice
Business | Incorrect Pricing strategy for the market | Failure to understand the market and demand for services Failure to connect with clients to understand capacity to spend Failure to understand competitors and their pricing | Significant loss of reputation and client fees
Business | Increased risk of fraud | Failure to put in place processes which clearly outline roles and responsibilities and identify risks and mitigating controls | Loss of reputation and supporting funds to grow and sustain the business
Business | Uninsured loss due to flood or fire | Damage to property not covered under policy, e.g. policy covers fire but not water damage from fighting fire in adjacent office. | Cost to business Serious disruption to service Possible failure of business
Business | Failure to manage conflict of interest | A major dispute between clients, e.g. divorce, family dispute, business owners | Cost to business Serious disruption to service Possible failure of business
Business Continuity | Loss or serious impairment of key Partner/Practitioner | Inadequate training, inadequate compensation, death, mental illness, substance abuse. | Loss of key business intelligence, inability to service clients (e.g. where partner is only RCA or RTA) Lack of continuity of client service
Business Continuity | Loss or damage to office premises, office equipment and/or client records | Natural catastrophe, e.g. fire, flood, earthquake | Serious disruption to service Possible failure of business
Financial | Failure to fully recognise revenue | Inaccurate recording of time spent on client work | Loss of revenue Failure of practice
Financial | Significant unexpected change in practice overheads | Change in market conditions Failure to monitor and/or negotiate supplier agreements | Partnership profitability reduced Failure of practice
Financial | Failure to collect receivables in a timely manner | Slow payment from debtors Lack of monitoring of outstanding debtors | Poor cashflow Outstanding debts become uncollectable Loss of revenue
Financial | Significant loan commitment not supported by business model | Over estimating value of goodwill and borrowing based on estimate Use inflated goodwill calculation when paying our departing Partners | Inability to service loan Reduction in value of goodwill
Financial | Failure to monitor partnership distribution agreements | Dispute between partners regarding contribution to the firm revenues and/or distribution of profits | Serious disruption to service Possible failure of business
Governance | Business strategy does not accommodate changing market conditions | Failure to plan for changing market conditions Activities of competitor Insufficient research and/or understanding of key markets | Loss of clients Reduction in market share
Governance | Failure to make or execute strategic decisions in a timely manner | Ineffective execution of strategy by leadership Lack of accountability Objectives of practice not clearly documented Lack of communication throughout the practice of strategies and objectives | Loss of market share Failure to capitalise on opportunities Poor partner/staff retention
Governance | Disengagement of Partners over change strategy | Partner(s) not identifying with Firm's strategy | Partners acting in self-interest over Firm strategy Partner(s) leaving Firm Loss of client fees Pressures on fixed overheads
Governance | Lack of cooperation between service areas | Remuneration model encourages excessive internal competition | Technical expertise not fully utilised Increased likelihood of claims Poor partner retention Loss of client fees
Human Resources | Failure to provide appropriate training and skill development for staff | Budget and time pressures reduce opportunity for necessary training Not effectively identifying training requirements | Damage relationship with client through sub-standard service delivery Poor staff retention Increased likelihood of claims
Human Resources | Inadequate staff numbers to provide high quality services | Unavailability of experienced qualified employees | Poor client services Loss of clients Increased likelihood of claims
Human Resources | Failure of HR/firm policy to meet legislative requirements | Unfair dismissal or sexual harassment claim | Cost to practice Lower staff morale
Human Resources | Increase in Workers' Compensation claims | Inadequate training and monitoring of OH & S policies | Penalties and fines Increased scrutiny from regulators
Human Resources | Increase in staff turnover and therefore loss of knowledge | Inadequate training, inadequate compensation | Loss of key clients, Loss of knowledge of key clients
Regulatory | Failure to comply with regulatory, legal and policy obligations | Lack of monitoring/understanding of legislative obligations | Penalties and fines Increased scrutiny from regulators Reputational damage
Technology | Failure to backup client data and records | No or inadequate data backup plan in place | Loss of client records Poor client service Loss of clients
Technology | Security of data compromised | Target of criminal hacker Insider threat for business | Loss of client records Poor client service Loss of clients
Technology | Disruption to provision of services | Technology service interruption No or inadequate disaster recovery plan | Cost to practice Poor client service Loss of clients
Technology | Failure of IT systems to meet the needs of the business | No IT strategy which is aligned and considers the requirements of the business | Poor client service Loss of clients
Technology | Lack of maintenance to office premises or improper usage of facilities | Water damage to IT equipment e.g. overflow from the floor above | Cost to practice Disruption to client service

## Assessment_Likelihood
Assessment Criteria − Likelihood
RATING | POTENTIAL FOR RISK TO OCCUR | PROBABILITY
ALMOST CERTAIN | Likely to occur several times a year | >90%
LIKELY | Likely to occur once a year | 50%-90%
POSSIBLE | Possibly occur once every few years | 10%-50%
UNLIKELY | Maybe occur once in 5 years | 5%-10%
RARE | Might occur once in 10 years | <5%

## Assessment_Consequence
Assessment Criteria − Consequence
RATING | IMPACT | FINANCIAL |  |  | OPERATIONAL | COMPLIANCE | STRATEGIC
|  | EBIT | Loss of market value | Disclosure | Scope | Legal/Regulatory | Reputational | Market Share | Strategy
CATASTROPHIC | Could shut down Practice/part of Firm. Business objectives not achieved. | >50% | >50% | Fiscal Year Restatement | Enterprise wide Inability to continue normal business operations across all business units | Management Indictments Large Scale Class Actions Regulatory Sanctions | Loss of confidence in all stakeholder groups | Potentially irrecoverable (i.e. 24-36 months) | Potential acquisition or bankruptcy
MAJOR | Material impact on Practice/Firm. Key business objectives not achieved. | 30%-50% | <50% | Fiscal Quarter Restatement | 3 Business Units Significant interruptions to business operations with 3 or more business units | Management challenges Large legal liability Regulatory fines | Loss of confidence by 3 or more stakeholder groups | Long term recovery (i.e. 12-24 months) | 2 or more changes in senior leadership Financial restructuring Significant changes to strategic plan
MODERATE | Noticeable impact on Practice/Firm. Some business objectives not achieved. | 15%-30% | <25% | Significant deficiency | 2 Business Units Significant interruptions to business operations with 2 or more business units | Regulatory fines Legal reserve established Regulatory investigation | Loss of confidence by 2 or more stakeholder groups | Mid term recovery (i.e. 6-12 months) | 1 or more changes in senior leadership Financial restructuring Significant changes to strategic plan
MINOR | Some impact that is easily remedied. | 5%-15% | <10% | Control weakness | 1 Business Units Significant interruptions to business operations with 1 or more business units | Management unaffected Minimal liabilities Regulatory attention | Loss of confidence by 1 or more stakeholder groups | Short term recovery (i.e. <6 months) | Refinements or adjustments to operating plans and execution
INSIGNIFICANT | Impact not visible. | <5% | <5% | Additional risk disclosure | Limited interruptions within 1 business unit | Limited liabilities or regulatory impact | Limited impact to 1 stakeholder group | Limited recovery (i.e. <3 months) | Limited adjustment necessary

## Rating Matrix
Risk Rating Matrix
CONSEQUENCE | Catastrophic | TOLERABLE | HIGH | VERY HIGH | VERY HIGH | VERY HIGH
| Major | LOW | TOLERABLE | HIGH | VERY HIGH | VERY HIGH
| Moderate | LOW | LOW | TOLERABLE | HIGH | HIGH
| Minor | VERY LOW | LOW | TOLERABLE | TOLERABLE | HIGH
| Insignificant | VERY LOW | VERY LOW | LOW | TOLERABLE | TOLERABLE
|  | Rare | Unlikely | Possible | Likely | Almost Certain
LIKELIHOOD

## Assessment_Controls
Assessment Criteria − Control Activity
RATING | ACTION | DESCRIPTION
NONE | Critical improvement opportunity | Controls and/or management activities are non-existent or have major deficiencies and don’t operate as intended.
NEEDS IMPROVEMENT | Significant improvement opportunity | Limited controls and/or management activities are in place, high level of risk remains.
ADEQUATE | Moderate improvement opportunity | Controls and/or management activities are in place, with opportunities for improvement identified.
STRONG | Limited improvement opportunity | Controls and/or management activities are properly designed and operating, with limited opportunities for improvement identified.
EFFECTIVE | Effective | Controls and/or management activities are properly designed and operating as intended.

## Treatment
Risk Treatment Options
Depending on the type and nature of the risk, the following options are available:
OPTION | TREATMENT
AVOID | Deciding not to proceed with the activity that introduced the unacceptable risk, choosing an alternative more acceptable activity that meets business objectives, or choosing an alternative less risky approach or process.
REDUCE | Implementing a strategy that is designed to reduce the likelihood or consequence of the risk to an acceptable level, where elimination is considered to be excessive in terms of time or expense.
SHARE | Implementing a strategy that shares or transfers the risk to another party or parties, such as outsourcing the management of physical assets, developing contracts with service providers or insuring against the risk. The third-party accepting the risk should be aware of and agree to accept this obligation.
TRANSFER
ACCEPT | Making an informed decision that the risk rating is at an acceptable level or that the cost of the treatment outweighs the benefit. This option may also be relevant in situations where a residual risk remains after other treatment options have been put in place. No further action is taken to treat the risk, however, ongoing monitoring is recommended.

## Lists (hidden)
Lists used in the Risk Register
Changing List Values
The Risk Register contains drop-down lists for the following entries:
Risk Category
Likelihood
Consequence
Control Effectiveness
Action
Status
To change the content of any drop-down list, refer to the information below.
If you do change a value in any drop-down list, remember to update the selections on the Risk Register for any risks already assessed.
Risk Categories
Under APES 325, at minimum risks should be considered within the following categories. If you add categories to the list below that may be relevant to your firm, you will need to update the cell naming defined as Risk_Category to ensure the any additions display in the drop-down lists on the Risk Register.
Governance
Business continuity
Business
Financial
Regulatory
Technology
Human resources
Stakeholder
Assessment Criteria & Ratings
To change the terminology for any of the criteria or ratings, make the edit to the lists below and then the remainder of the spreadsheet will automatically update.
| Likelihood | Consequence | Risk Rating | Controls
| ALMOST CERTAIN | CATASTROPHIC | VERY HIGH | NONE
| LIKELY | MAJOR | HIGH | NEEDS IMPROVEMENT
| POSSIBLE | MODERATE | TOLERABLE | ADEQUATE
| UNLIKELY | MINOR | LOW | STRONG
| RARE | INSIGNIFICANT | VERY LOW | EFFECTIVE
Treatment
To change the wording used for the treatment options, make the edit to the list below and then the remainder of the spreadsheet will automatically update.
Treatment
AVOID
REDUCE
SHARE
TRANSFER
ACCEPT
Status
To change the wording used for the status of risks, make the edit to the list below and then the remainder of the spreadsheet will automatically update.
Treatment
OPEN
CLOSED