## Project Schedule
This document is the Project Schedule for the Trade Show Promotion Project
It is part of the supporting assessment resources for Assessment Task 6 of BSBPMG532.
Week beginning
|  |  |  | Calendar | 2022-10-01 | 2022-10-08 | 2022-10-15 | 2022-10-22 | 2022-10-29 | 2022-11-05 | 2022-11-12 | 2022-11-19 | 2022-11-26 | 2022-12-03 | 2022-12-10 | 2022-12-17 | 2022-12-24 | 2022-12-31 | 2023-01-07 | 2023-01-14 | 2023-01-21 | 2023-01-28 | 2023-02-04 | 2023-02-11 | 2023-02-18 | 2023-02-25 | 2023-03-04 | 2023-03-11 | 2023-03-18 | 2023-03-25 | 2023-04-01
| Item | Topic | Activity | Responsible
Project start | bar: 2022-10-01
| 1 | Contract trade show materials provider
| 1.1 | Contract | Contact potential website developers | Project Manager | bar: 2022-10-01 to 2022-10-08
| 1.2 | Contract | Ask for quotes | Project Manager | bar: 2022-10-15 to 2022-10-22
| 1.3 | Contract | Review quotes | Project Manager | bar: 2022-10-15 to 2022-10-22
| 1.4 | Contract | Select most suitable quote | Project Manager | bar: 2022-10-22 to 2022-10-29
| 1.5 | Contract | Send contract to selected developer | Project Manager | bar: 2022-10-29
| 1.6 | Contract | Signed contract returned and file | Project Manager | bar: 2022-11-05
| 2 | trade show materials development
| 2.1 | Development | Set up initial meeting for discussion about Trade Show Promotion Project | Project Team | bar: 2022-11-12 to 2022-11-19
| 2.2 | Development | Confirm brief in writing | Project Team | bar: 2022-11-26
| 2.3 | Development | Develop copy for Brochures and booth design | Project Team | bar: 2022-12-03 to 2022-12-24
| 2.4 | Development | Weekly meetings to discuss progress | Project Team | bar: 2022-12-24
| 2.5 | Development | Final meeting to review | Project Team | bar: 2022-12-24
| 2.6 | Development | Final changes sent by email | Project Team | bar: 2022-12-24
| 2.7 | Development | Booth Finalised and delivered | Project Team | bar: 2022-12-24
| 2.8 | Development | Booth finalised and delivered revised date | Project Team | bar: 2022-12-31
| 3 | Website sign off
| 3.1 | Marketing | Final meeting to review | Project Team | bar: 2023-01-07
| 3.2 | Marketing | Final changes sent by email | Project Team | bar: 2023-01-07
| 3.3 | Marketing | Erect Booth at HQ to test for functionality | Project Team | bar: 2023-01-14
| 3.4 | Marketing | January trade show go-live | Project Team | bar: 2023-01-21
| 4 | Training
| 4.1 | Training | Identify and document training needs | Project Manager | bar: 2023-01-21 to 2023-01-28
| 4.2 | Training | Develop suggested program for training | Project Manager | bar: 2023-01-21 to 2023-01-28
| 4.3 | Training | Organise training | Project Manager | bar: 2023-01-21 to 2023-01-28
| 4.4 | Registration | Implement training | Website developer | bar: 2023-02-04 to 2023-02-11
| 4.5 | Registration | Evaluate training | Project Manger | bar: 2023-02-18
| 5 | Project completion
| 5.1 | Completion | Evaluation meeting | Project Team | bar: 2023-02-25
| 5.2 | Completion | Lesson learned report and action | Project Team | bar: 2023-02-25
| 5.3 | Completion | Action plan implemented | Project Team | bar: 2023-03-04 to 2023-03-11
Assessor instructions:
Students must reflect the booth finalised and delivered revised date extended by one week - to 31 Dec.
Students must save the update report with the new file name Project Schedule_dd.mm.yy