## Sheet1
Site Address: |  |  |  |  | Legend: |  |  |  | Critical path | [5 empty] | Non work day | [5 empty] | Weekend
Commencement Date: | [8 empty] | Public holiday | [5 empty] | Inspection
Completion Date:
Scheduled Works | Length for Task (days) | Human Resources Required | Materials Supplier | Plant and Equipment Required | Week 1 | [5 empty] | Week 2 | [5 empty] | Week 3 | [5 empty] | Week 4 | [5 empty] | Week 5 | [5 empty] | Week 6 | [5 empty] | Week 7 | [5 empty] | Week 8 | [5 empty] | Week 9 | [5 empty] | Week 10 | [5 empty] | Week 11 | [5 empty] | Week 12 | [5 empty] | Week 13 | [5 empty] | Week 14 | [5 empty] | Week 15 | [5 empty] | Week 16 | [5 empty] | Week 17 | [5 empty] | Week 18 | [5 empty] | Week 19 | [5 empty] | Week 20 | [5 empty] | Week 21 | [5 empty] | Week 22 | [5 empty] | Week 23
[5 empty] | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S | M | T | W | T | F | S
<remove work tasks not required> | <update based on project> | <update based on project> | <update based on project> | <update based on project> | Week 1 M: <update based on project>
Site works
Site investigation |  | Builder
Site set out |  | surveyor
Temp fence/toilet/shed |  | builder/hire company |  | Fencing, toilet, site shed
Temp power pole |  | electrician |  | Kennards for temp power pole.
Concrete slab and footings
Clear site, sediment control |  | plant/operator/ builder |  | Digger, truck
Set out |  | builder/chippy |  | Hurdles, scrap timber, string lines
Excavate/stockpile |  | plant/operator |  | Digger, truck
Excavate footings |  | plant/operator |  | Digger, truck
Plumbing/electrical services |  | plant/operator/elec/plumber |  | PVC pipe, electrical cable, conduit
Formwork/sand/plastic/steel |  | concreters |  | Sand, plastic, mesh, timber,
Pre-slab/Footing inspection |  | building inspector
Termite controls |  | termite contractor |  | Pesticides- various chemicals supplied
Pour slab |  | concreters |  | Concrete pump supplied, wheel barrows, finishing equipment
Slab cure
Slab inspection |  | building inspector
Strip boxing |  | concreters |  | Hand tools
Frame stage
Chalk out |  | carpenter |  | Hand tools, chalk line
Termite controls
Frame walls |  | carpenter |  | Nail gun, nails, leveling tools, drop saw, hand tools
Brick Gar |  | brick layer |  | Hand tools, mixer, sand, shovel, wheel barrow
Frame roof |  | carpenter |  | Timber, drop saw, nail gun, nails, fixing brackets.
Frame inspection |  | building inspector
Fascia/gutter |  | roof plumber |  | Guttering, tin snips, hand tools,
Lock up stage
Fall protection |  | scaffolder |  | Podger hammer, scaffolding supplied, forklift
Roof tiles |  | roof tilers |  | Tiles supplied by Bristile, conveyor, roof tiler hand tools
Scaff down |  | scaffolder |  | Truck, fork lift,
Windows install |  | carpenter |  | Hand tools, drill, nails - bullet heads.
Wrap house |  | bricklayer |  | House wrap, staples, stapler
Brick house |  | bricklayer |  | Bricks supplied, sand, bricklayers hand tools, wheel barrows
Eaves/infils |  | carpenter |  | Sof sheet nails, cement sheets, joining strap
External door/gable clad |  | carpenter |  | Door and cladding supplied, cement sheet for gable
Brick clean |  | brick cleaner |  | Cleaning supplies + tools required for cleaning process
Plumbing rough in |  | plumber |  | PVC pipe, hand tools, power tools,
Straighten walls/bath hob/shower |  | carpenter |  | Electric planar, straight edge, level, hand tools
Electrical rough in |  | electrician |  | Hand tools, power tools, cable, connectors.
HVAC rough in |  | air con |  | Ducting, hand tools, duct tape
Plasterer/alfresco |  | plasterer |  | Plaster, hand tools, power tools, glue
Water proofing |  | waterproofer |  | Waterproofing, matting,
Kitchen |  | cabinet maker |  | Pre made cabinets, power tools, hand tools
Lock-up inspection
Fitout
Fix carpentry |  | carpenter |  | Power tools, skirts, arcs, hand tools, fixing gun
Painting |  | painter |  | Paint, primer
Tiling |  | tiler |  | Tiles supplied, grout, adhesive
Door furniture |  | carpenter |  | Door furniture supplied, hand tools and power tools from amg
Install applications |  | plumber/election |  | Power tools and hand tools
Elecrical fit off |  | electrician |  | power tools, hand tools, connectors
Plumbing fit off |  | plumber |  | Fit off items, power tools, hand tools
Stormwater/drainage |  | plumber |  | Down pipes, drainage pits.
HVAC fit off |  | aircon |  | Power tools
Shower screen/mirror |  | shower screen |  | Drill, caulking gun, adhesives
Bath fittings |  | plumber |  | Bathroom fittings, hand tools and power tools
Garage door |  | Gar Door |  | Power tools, lift to hoist door from Kennards
Builders clean |  | labourer |  | buckets
Caulking |  | labourer |  | Caulking gun, caulk
Carpet |  | carpenter |  | Hand tools, cutting tools
Final practical completion inspection/ Certificate of Occupancy |  | building inspector
Defects |  | client/ builder
Final clean |  | builder/labourer |  | Final clean products
Remove temp fence |  | hire
Fixing stage inspection
Handover |  | builder