## Gantt Chart
[6 empty] | 1 |  | 0 | 2021-02-22 | 2021-03-01 | 2021-03-08 | 2021-03-15 | 2021-03-22 | 2021-03-29 | 2021-04-05 | 2021-04-12 | 2021-04-19 | 2021-04-26 | 2021-05-03 | 2021-05-10 | 2021-05-17 | 2021-05-24 | 2021-05-31 | 2021-06-07 | 2021-06-14 | 2021-06-21 | 2021-06-28 | 2021-07-05 | 2021-07-12 | 2021-07-19 | 2021-07-26 | 2021-08-02
New Convenience Store at Mudgee | bar: 0
Time Period
Weekly
| Gantt Chart Dates |  |  |  |  | Yellow - Project completion date
| Beginning Date | 2021-02-22 |  |  |  | Green - Complete Project
| Proposed completion date | 2021-07-22
[5 empty] | Contingencies: | Factor in possible delays
2021
[8 empty] | % | Feb | Mar | Mar | Mar | Mar | Mar | Apr | Apr | Apr | Apr | May | May | May | May | May | Jun | Jun | Jun | Jun | Jul | Jul | Jul | Jul | Aug
| Scheduled Works | Human Resource Required | Plant and Equipment Required | Task Duration (Day) | Start Date | End Date | Comments regarding contingencies | Complete | 22 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2
1 | Site works | Task Owner |  | Formula |  |  |  | %: 100%
| Site investigation | Builder |  | 1 |  |  |  | %: 100%
| Site set out | Surveyor |  | 1 |  |  |  | %: 100%
| Temporary fence/toilet/shed | Builder/hire company | Fencing, toilet, site shed | 1 |  |  |  | %: 100%
| Temporary power pole | Electrician | Kennards for temporary power pole | 1 |  |  |  | %: 100%
2 | Concrete slab and footings | [6 empty] | %: 100%
| Clear site, sediment control | Plant/ operator/ builder | Digger, truck | 2 |  |  |  | %: 100%
| Set out footings and slab | Builder/ Concreters | Hurdles, steel reinforcing bars, stringlines | 2 |  |  |  | %: 100%
| Excavate/stockpile | Plant operator | Digger, truck | 1 |  |  |  | %: 100%
| Excavate footings | Plant operator | Digger, truck | 1 |  |  |  | %: 100%
| Plumbing/ electrical services | Plant operator/ electrician/ plumber | PVC pipe, electrical cable, conduit | 2 |  |  |  | %: 100%
| Formwork/sand/plastic/steel | Concreters | Sand, plastic, mesh, timber | 4 |  |  |  | %: 100%
| Pre-slab/Footing inspection | Building inspector |  | 1 |  |  |  | %: 100%
| Termite controls | Termite contractor | Pesticides- various chemicals supplied | 1 |  |  |  | %: 100%
| Pour slab | Concreters | Sand, plastic, mesh, timber | 1 |  |  |  | %: 100%
| Slab cure |  |  | 7 |  |  |  | %: 100%
| Slab inspection | Building inspector |  | 1 |  |  |  | %: 100%
| Strip boxing | Concreters | Hand tools | 1 |  |  |  | %: 100%
3 | Frame stage | [6 empty] | %: 100%
| Chalk out | Carpenters | Hand tools, chalk line | 1 |  |  |  | %: 100%
| Frame walls/ External walls | Carpentry / Brickwork | Nail gun, nails, leveling tools, drop saw, hand tools | 5 |  |  |  | %: 100%
| Frame walls/ Internal walls | Carpentry / Brickwork | Nail gun, nails, leveling tools, drop saw, hand tools | 2 |  |  |  | %: 100%
| Frame roof structure | Building inspector |  | 2 |  |  |  | %: 100%
| Fascia/gutter | Roof plumber | Guttering, tin snips, hand tools | 2 |  |  |  | %: 100%
| Windows install | Carpenters | Hand tools, drill, nails - bullet heads | 3 |  |  |  | %: 100%
| Frame inspection | Building inspector |  | 1 |  |  |  | %: 100%
4 | Lock up stage | [6 empty] | %: 100%
| Fall protection | Scaffolder | Podger hammer, scaffolding supplied, forklift | 1 |  |  |  | %: 100%
| Roof tiles | Roof tilers | Tiles supplied by Bristile, conveyor, roof tiler, hand tools | 3 |  |  |  | %: 100%
| Wrap house (sisalation) | Bricklayer | House wrap, staples, stapler | 1 |  |  |  | %: 100%
| External claddings | Cladding installer | Hand tools, cladding material | 4 |  |  |  | %: 100%
| Eaves/infils | Carpenter | Soft sheet nails, cement sheets, joining strap | 2 |  |  |  | %: 100%
| Plumbing/ electrical rough in | Plumber | PVC pipe, hand tools, power tools | 3 |  |  |  | %: 100%
| Scaffold down | Scaffolder |  | 1 |  |  |  | %: 100%
| External door/ gable cladding | Carpenter | Door and cladding supplied, cement sheet for gable | 3 |  |  |  | %: 100%
| HVAC rough in | Air con | Ducting, hand tools, duct tape | 2 |  |  |  | %: 100%
| Plaster | Plasterer | Plaster, hand tools, power tools, glue | 5 |  |  |  | %: 100%
| Lock-up inspection | Building inspector |  | 1 |  |  |  | %: 100%
5 | Fitout | [6 empty] | %: 100%
| Internal architraves and doors | Carpenter | Hand tools,door supplies | 2 |  |  |  | %: 100%
| Electrical works | Electrical | Hand tools, power tools, cable, connectors | 5 |  |  |  | %: 100%
| Water proofing | Waterproofer | Waterproofing, matting | 4 |  |  |  | %: 100%
| Tiling | Tiler | Tiles supplied, grout, adhesive | 5 |  |  |  | %: 100%
| Stormwater/drainage | Plumber | Down pipes, drainage pits. | 3 |  |  |  | %: 100%
| Plumbing fit off | Plumber | Fit off items, power tools, hand tools | 4 |  |  |  | %: 100%
| HVAC fit off | Aircon | Power tools | 2 |  |  |  | %: 100%
| Bathroom fittings | Plumber | Down pipes, drainage pits. | 1 |  |  |  | %: 100%
| Painting | Painter | Paint, primer | 5 |  |  |  | %: 100%
| Caulking | Labourer | Caulking gun, caulk | 2 |  |  |  | %: 100%
| Final practical completion inspection/ Certificate of Occupancy | Building inspector |  | 1 |  |  |  | %: 100%
| Defects | Client/builder | Final clean products | 1 |  |  |  | %: 100%
| Remove temporary fence | Hire |  | 1 |  |  |  | %: 100%
| Fixing stage inspection | Building inspector |  | 1 |  |  |  | %: 100%
| Handover | Builder |  | 1 |  |  |  | %: 100%
6
Exclude Weekends
Task Duration Calculation
Include Weekends
Key